## BA Planning Tool
Title
Owner
Version
Status
# | Activity | Estimated Effort | Start Date | End Date | Status | Who Involved | Guidelines
Step 1: Get Oriented
| Clarify the BA role | [5 empty] | Clarify the primary goal for the BA to fulfill, what your inputs will be, what deliverables you will be responsible for, and who receives the output of your work.
| Determine your primary stakeholders | [5 empty] | Start with your business sponsor and manager - expand out from there.
| Understand the project history | [5 empty] | Use document analysis and interviews to discover what's already happened so you can pick up the project at the most appropriate stage.
| Understand the existing technology systems | [5 empty] | Don't over-invest in this step. You can always come back later and learn more once scope is clarified.
| Understand the existing business processes | [5 empty] | Don't over-invest in this step. You can always come back later and learn more once scope is clarified.
Step 2: Discover the Primary Business Objectives
| Review existing documentation about the business objectives. | [5 empty] | This may be contained in a business case, scope statement, or other high-level project planning document.
| Interview primary business sponsor about the business objectives. | [5 empty] | This activity will often be a good first step, especially when no documentation is available.
| Choose one or more appropriate techniques to discover the business objectives. | [5 empty] | Options include: document analysis, interviews, observation, root cause analysis, brainstorming, prototypes, and walk-throughs.
| Analyze business objectives to ensure they are clear and actionable. | [5 empty] | Warning - don't commit to solving business problems, only to understanding and communicate those problems.
| Finalize business objectives and add to appropriate documentation. | [5 empty] | Be sure to get to the problem behind any solutions that are presented by stakeholders.
| Placeholder: Invest in stakeholder relationships. | [5 empty] | Step 2 is an ideal time to make stakeholder relationships a conscious and deliberate priority. Add activities here to invest in your relationships.
Step 3: Define Scope
| Define the solution approach | [5 empty] | Consider both technical and business process solution approaches. Collaborate heavily with members of the project and business teams.
| Use analysis techniques to analyze scope | [5 empty] | Common options include: System Context Diagram, Data Flow Diagram, High-Level Process Model, Use Case Diagram.
| Draft a scope statement | [5 empty] | Your project's scope statement may be included in one of many deliverables.
| Prioritize requirements / features | [5 empty] | Link all requirements/features to business objectives and prioritize or rank the requirements.
| Validate the scope statement | [5 empty] | Ensure there is a shared ownership of what's in and out of scope for the product or project.
| Confirm the business case | [5 empty] | Ensure the scope that's defined will deliver a positive ROI for your organization.
Step 4: Formulate the Business Analysis Plan
| Identify the types of business analysis deliverables required for this project | [5 empty] | Take your project methodology and project scope into account.
| Define the BA deliverables list | [5 empty] | Define a set of deliverables that completely covers the scope of your project. Use the Deliverables List tab in this template to capture a complete list of deliverables.
| Identify project stakeholders | [5 empty] | For each deliverable, identify stakeholders who need to be involved.
| Identify timelines for each deliverable | [5 empty] | Take into account important assumptions such as stakeholder availability and deliverable complexity (and be sure to list your assumptions with each deliverable on the next tab).
| Gain buy-in on the business analysis plan | [5 empty] | Pay close attention to any stakeholders who will be heavily involved in the business analysis effort.
Step 5: Define the Detailed Requirements
| This section may be replaced with your deliverables list. If creating a work break-down structure, consider each of the following tasks for each deliverable: | [5 empty] | Good approaches for sequencing deliverables include working to the critical path, reducing ambiguity and complexity, and generating quick wins.
| Elicit information | [5 empty] | Consider different techniques, including interviews, observation, prototyping, and document analysis.
| Analyze information and draft the deliverable | [5 empty] | As you create your draft, generate a list of questions for your business stakeholders and implementation team.
| Review and validate the deliverable | [5 empty] | A simple deliverable may have 1 or 2 review cycles, a complex deliverable or deliverable set could require several cycles.
| Finalize the deliverable | [5 empty] | This means that the deliverable is ready for the next step in the design or implementation process. As you finalize, take a step back and consider whether you've increased the scope of your project within this deliverable.
Step 6: Support the Technical Implementation
| Review the solution design | [5 empty] | Ensure the design fulfills all of the requirements. See if there is potential to fulfill any new business objectives that originally seemed infeasible.
| Review test plans / test cases | [5 empty] | Ensure the test cases will confirm the requirements. If your test lead was not able to sit in on the final requirements review sessions, plan for time to walk them through the requirements documentation.
| Be available for questions / issues | [5 empty] | While these can't be planned in advance, it's a good idea to allocate a certain number of hours each week to address questions and issues once the technical implementation and test processes begin.
| Revise requirements / manage requirements changes | [5 empty] | Plan a small amount of time to manage small changes related to minor issues. Update your plan as any significant new issues surface and estimate them separately.
| Lead user acceptance testing | [5 empty] | If responsible for this set of activities, consider breaking out tasks for planning the UAT process, creating test scenarios/cases, and managing the UAT process.
Step 7: Help the Business Implement the Solution
| Process Development | [5 empty] | Create or complete any future state business process models. After the technical implementation plan is well understood, newly impacted business processes may be uncovered.
| Training | [5 empty] | Consider training requirements both for existing employees who need to understand what is changing and new employees.
| Update organizational assets | [5 empty] | Extend or create a copy of the deliverables list to capture any orgaizational assets, such as email templates, forms, help files, and system documentation that need to be updated to reflect the technology and business process changes.
| Manage business-driven change requests | [5 empty] | Plan a small amount of time to manage small changes related to minor issues. Update your plan as any significant new issues surface and estimate them separately.
| Support the implementation roll out | [5 empty] | Consider reviewing the roll out plan, identifying interim business process, and possibly being available during or after the roll out.
Step 8: Assess the Value Created by the Solution
| Evaluate progress against business objectives | [5 empty] | Consider both qualititative and quantitative ways of assessing progress.
| Measure the results | [5 empty] | When possible, compile reports comparing the original state to the new and hopefully improved state of the organization.
| Communicate the results | [5 empty] | Collaborate closely with key stakeholders. Consider how you can celebrate and share the results with the project team and throughout the organization.
| Suggest follow-up projects and initiatives | [5 empty] | Consider initiatives to realize the intended results of this project or new potential benefits enabled by this project.
| Evaluate your business analysis process | [5 empty] | Consider what learnings you want to take with you on future projects and what improvements you'll make.
PROJECT SUMMARY |  | Total Hours | Start Date | End Date |  |  | Use this row to show the overall timeline of the BA effort.
|  | 0 |  |  |  |  | Total hours calculates all estimated hours. Manually add in the start date and end date based on the first and last date of your tasks.
Note on C7: : Identify the estimated effort to complete this activity, often captured in hours.
Note on D7: : Identify the date you expect this activity will be able to start.
Note on E7: : Identify the date you expect this activity will be completed.
Note on F7: : Common options include: Not Started In Progress Complete
Note on G7: : Identify any stakeholders who need to be involved in this activity.

## Deliverables List
Title
Owner
Version
Status
# | Deliverable Name | Estimated Effort | Start Date | End Date | Status | Who Involved | Assumptions
Note on C7: : Identify the estimated effort to complete this activity, often captured in hours.
Note on D7: : Identify the date you expect this activity will be able to start.
Note on E7: : Identify the date you expect this activity will be completed.
Note on F7: : Common options include: Not Started In Progress Complete
Note on G7: : Identify any stakeholders who need to be involved in this activity.
Note on H7: Laura: Identify assumptions behind your estimate and timeline such as stakeholder availability, compexity, or items out of scope.