## Scope
ExampleApp
Feature List
ID | Feature | Description | Priority | Dev Estimate (man days) Baseline Scope (Must & Should) | Dev Estimate (man days) Baseline Scope (Other) | Dev Estimate (man days) Removed Scope | Dev Estimate (man days) Added Scope | Dev Estimate Notes | Elab Complete (%) | Dev Complete (%) | Status Notes
F059 | Submission e-mails to applicants | E-mail to applicant to say "thank you for submitting your ExampleApp - now wait for approval". Different template per org type possibly | Should | 2 |  |  |  |  | 100% | 100%
F060 | Submission warning | Pop-up asking user to confirm that they want to submit and remind them that submission is final Also make it clear who the submission e-mail will be sent back to | Should | 2 |  |  |  |  | 100% | 100%
F061 | Approval e-mail log | When approval e-mail sent, log this fact in the "comments" box of the status history table | Should | 1 |  |  |  |  | 100% | 100%
F074 | Squiddlecy e-mail templates | Changes to Squiddlecy e-mail templates as requested by Nardle (Bhong mIGht have an e-mail on this) - needs to have different helpdesk details | Should | 1 |  |  |  |  | 100% | 100%
F075 | Squiddle "not relevant" req'ts | Add "not relevant" option to Squiddle req'ts 118; 119 (Gary says not 318) | Must | 0.5 |  |  |  |  | 100% | 100%
F001 | Less painful timeout | Either extend timeout or find some other way of making it less obstructive (e.g. make it visible even if you are using another application at the time) | Must | 0.5 |  |  |  |  | 100% | 100%
F014 | Editable comments field | Amend comments field (currently only possible to add new comments) Prior to submission only - comments locked once assessment submitted | Must | 4 |  |  |  |  | 100% | 100%
F004 | widget authoring | Replace existing "feeder files" with something which (a) removes unnecessary duplication (b) auto-generation of documents (c) manages version control better Current thinking is MS Access tool with data structure similar to ExampleApp database Will require tools to mIGrate/copy database | Must | 14 |  |  |  | Assume MS Access tool being produced separately - just need mIGration tool | 100% | 100%
F008 | Evidence tick boxes | Mark individual items of evidence as "obtained" Add comments re. the evidence obtained Mandatory for trusts but optional for other orgs e.g. PDs i.e. can choose to just score the attainment levels manually Each required piece of evidence is mandatory When all relevant evidence obtained, automatically increase attainment level Add custom evidence types | Must | 18 |  |  |  | Data structure 3 days New Evidence screen 5 Change widgets screen 5 days Uncertainties 5 | 100% | 100% | Not done evidence review screen for HIP team
F009 | Upload evidence | Upload evidence documents to ExampleApp Linked to "evidence tick boxes" feature Various doc types (doc, pdf, xls, msg etc.) Virus checker required? | Must | 8 |  |  |  |  | 100% | 100% | Not done virus checker
F005 | Single document per widget | Combine on-screen info, guidance document and checklist into a single "document" for each widget | Must | 12 |  |  |  | PDF format - statically generated at release time (e.g. UsIGn FOP) | 100% | 100%
F006 | Remove dual maintenance of knowledge base links | Remove need to dual maintain knowledge base links both in the knowledge base spreadsheet and in guidance documents Ties in with "widget authoring" and "single document per widget" in terms of auto generating widgets documentation | Must | 15 |  |  |  | Need to put KB in Access DB and rewrite KB import util | 100% | 100%
F016 | "Not Relevant" audit trail or ability to make it available on a case-by-case basis | The system is confIGured such that organisations are allowed to answer “not relevant” to some widgets but not to others. Sometimes, an organisation will agree with the HIP Team manager that a particular widget is not relevant to them even though the system insists that it is. In this case they mark the widget as fully satisfied (3 points) and add a comment as audit trail. This feature would improve the audit trail in some way (not currently clear how exactly). DPI team able to go into specific org assessment and mark specific req't as "not relevant option available" | Must | 4 |  |  |  |  | 100% | 100%
F002 | HIGhlIGht key widgets | HIGhlIGht the key widgets in all appropriate places, including: - widgets lists - Individual widget screens - Guidance documents - Reports - Assessment summary screen (%age of key widgets complete) (some details in e-mail from XXX 14/08/09) | Must | 3 |  |  |  |  | 100% | 100%
F057 | widget derivations | Include info on the derivation of each widget (in the guidance sheet?) | Must |  |  |  | 1 |  | 100% | 100%
F071 | Get rid of "obsolete" categorisations | Remove reference to HORUS and/or MSPrPe and/or "Category" from widgets Beware though - HORUS has some link-in with DTB which mIGht need changing too Also need to remove MSPrPe from Assessment Report | Must |  |  |  | 6 | Estimate excludes DTB and removing data structures | 100% | 100% | Need to check DTB impact
F007 | Bulk download/print widgets documents | Download and/or print all widget documentation Maybe as a single (consolidated) document or as a bundle of documents (probably the former to allow bulk printing) Format mIGht be HTML, Word or PDF (to be decided) Probably only require to download widget set for a single org type (i.e. not a consolidated file of all widgets for all org types) | Must | 4 |  |  |  | Dependent on F0005 | 100% | 100%
F010 | Export to XL (simple data feed) | Create an XL sheet of "the widget set" for a given org type Includes (probably) all metadata for the widget set - attainment levels, evidence lists etc. Download as a simple CSV file. | Must | 4 |  |  |  |  | 100% | 100%
F003 | Bulk e-mail notifications | Send e-mail to ExampleApp users Filter by org type, role Filter by assessment status (e.g. In Progress) Users *cannot* opt out Format e-mail (e.g. RTF) (Should) Include attachments (Must) Exclude users with lockec accounts Specify date/time to sent e-mail (Could) Cater for WARP widgets (ref. Alistair Donalsdon) Note: PQRMail limits number of recipients per e-mail so Outlook integration mIGht not be the solution here | Must | 10 |  |  |  |  | 100% | 100%
F012 | Better navIGation/usability | General overhaul of website look and feel/usability/navIGation. Under consideration: - Simplify home page - Clearer log in process (including "request registration" tab - Virtual tour/training/quick start guide - Simplified PD interface - Move nav bar to left or top - Easier navIGation through widgets (e.g. no need to scroll to click "Next") - Can't currently re-save a score - have to exit and re-enter the widget - Re-branding (either new PQR EFG style or DXX style) - ISOxxx page - better name and layout | Must | 20 |  |  |  | Time boxed | 100% | 100% | Will need to do a sweep of all pages once the new look & feel is implemented
F013 | Accessibility | Ensure WAI compliance (single-A or double-A) | Must | 10 |  |  |  | Time boxed | 80% | 80% | I think we could do more on this
F017 | Report - Status summary | One page summary report on own organisation's status, suitable to print/send to e.g. Board - current %age score (where not answered = 0) - target %age score - RAG status - (perhaps) breakdown by category | Must | 5 |  |  |  | includes Organisation Dashboard | 100% | 100%
F075 | Reports: status report extra | Status report to show progress against baseline and performance update scores | Must |  |  |  | 2 |  | 100% | 100%
F065 | Review at baseline and perf update | Scores to be reviewed before submitting a baseline or performance review Not sure if this is a good idea Or maybe this is "remove undo baseline" or something else | Must |  |  |  | 2 |  | 100% | 100%
F067 | GHI reminders | Send annual reminders to GHIs (and other mid-year submitteds) to complete their ExampleApp | Must |  |  |  | 4 |  | 100% | 100% | Need to amend GHI approval email
F068 | Org type descriptions | Provide better descriptions of org types so it's easier to tell which applies to who (could tie up with DTB org types too) | Must |  |  |  | 1 |  | 100% | 100%
F078 | Target Level clarity | Make it clear what the target level is for - is it for this year, next year, or doesn't it matter? Make it clear that it ties into improvement planning | Must |  |  |  | 1 |  | 100% | 100%
F086 | Glossary of terms | Glossary of terms (maintained in RATty) with ability to hyperlink through from widgets text | Must |  |  |  | 11 |  | 100% | 100%
F015 | Better CCN/show changes online | Better hIGhlIGhting of which widgets have changed For example, mark up changes in manner similar to MS Word "track changes" Possibly a flag per widget indicating whether it has changed since last year | Should | 7 |  |  |  | Assume manual markup of text | 100% | 100% | Just need to link CCN into various pages
F019 | Online improvement plan | AssIGn widget to user AssIGn improvement plan item to user AssIGn evidence item to user Allocate deadline for assIGned item Send e-mail reminder to assIGned user Keep audit trail of who completed what and when Add custom actions Produce reports as appropriate Export to XL | Should | 25 |  |  |  |  | 80% | 80%
F091 | Report: Evidence gap analysis | Report showing which evidence is "missing" against the standards. Actually this sounds a lot like an automated improvement plan | Should |  |  |  | 0 | Dev estimate already included in F019 | 100% | 100%
F092 | Evidence report | A report or view listing all evidence submitted and against which widgets - rather than having to go into each widget individually. Useful when a new version of a document is issued to quickly find out where it is referenced. | Should |  |  |  | 0 | Dev estimate already included in F019 | 100% | 100%
F021 | More flexible role admin | Allow PQR Business Partners to create multiple users per organisation | Should | 2 |  |  |  |  | 100% | 100%
F024 | Remove outdated KB information | Review knowledge base and remove outdated documents | Should | 0 |  |  |  | HIP team job
F085 | Squiddlecy parent organisation | e.g. Link all Boyds outlets to their HQ (in simliar way to XYZ being the parent) | Should |  |  |  | 6 |  | 100%
F083 | Capture reason for status rollback | Ability for HIP team to capture the reason they rolled back an assessment status e.g. "unsubmitted because insufficient evidence supplied for widget 8" | Should |  |  |  | 3
F096 | IntellIGent email address checker | Email validator applies simple rules like having a list of known domain names and either warning or refusing to register you if it's not on the list. Also could check name spelling against forename and surname | Should |  |  |  | 1 |  | 100%
F095 | Change cube reports | Due to licence issues only Nardle has access to the Cube reports. Are there any alternatives which give access to all? Also the Cube is "unreliable" (quote CK) 22/3/10 CC says previously looked into getting extra licences but procurement had issues because ProClarity now subsumed into MS JHYrePoint (not clear what the actual issue was - maybe check with Nardle) | Could |  |  |  | 5
F062 | PD's XYZ details | Ability for XYZ to provide details of a contact person for PDs in their area - this mIGht be a case of identifying which XYZ user deals with PDs - and making this visible to PDs (also for Dentists and Squiddles) | Could |  |  |  | 4
F080 | Reports: replicate DTB reports | Do we want to replicate the XYZ reports that are currently available in DTB? | Could |  |  |  | 10 |  | 100% | 100%
F023 | Annual confirmation of contact details | Each year force users to confirm their contact details (e-mail address, phone number) | Could | 5 |  | 5
F102 | widget-level audit flag | Ability for ExampleApp admin to mark a widget as having been audited and by whom (e.g. internal/external) | Won't |  |  |  | 2
F026 | KB - "last reviewed date" | Record and display "date last reviewed" for each document (give user confidence that document is still relevant) | Could |  | 2 |  |  |  | 50% | 50% | Needs adding to req details page/PDF
F027 | KB - Rating system | User rates and reviews KB documents (a la Amazon) | Could |  | 10
F028 | Organisation dashboard | Improved assessment summary screen including e.g. %age score and RAG indicator | Could |  | 0 |  |  | Icluded in Status Report | 100% | 100%
F029 | Better info for GHIs | Add exemplar documents to KB Provide evidence checklists | Could |  | 0 |  |  | HIP team work
F030 | Simplify/shorten/quicken | Further simplify terminoloIG and wording of widgets/guidance, especially for PDs Also, make wording more applicable to primary care | Could |  | 0 |  |  | HIP team work
F031 | Get rid of user-defined views | Nobody uses it (find out for sure) | Could |  | 2 |  |  |  | 100% | 100%
F032 | Deadline countdown | Indicator (perhaps graphical) on home page showing the user how long they have left before the next milestone date e.g. submission. | Could |  | 4 |  |  |  | 100% | 100%
F033 | Define resources to attain next level | Enhancement to online action plan Capture cost/time/people required to achieve an attainment level - which all goes towards a risk-based decision as to whether to do it or not | Could |  | 8
F034 | Report - XYZs monitoring GHIs | Available to XYZ users to monitor GHIs and other service providers Implies linkage between GHIs and XYZs And a minatennace screen for XYZs to maintain them Plus a business process to identify the linkage at the point of aplication (PRMB) Plus a mIGration activity for existing GHIs Are XYZGYLeads even supposed to monitor GHIs? Also suggested by Peter Conoulty, Liverpool XYZ (See email 26/01/10 from Vanessa) | Could |  | 4
F035 | Report - favourites | Save common reports and re-produce them without have to re-build them each time | Could |  | 10
F036 | Report - Email | Ability to email reports to colleagues (or at least make it clear how to do it) | Could |  | 18
F037 | Report - XL integration | Download reports in XL (not CSV) format complete with formatting/colours | Could |  | 20 |  |  |  | 50% | 50% | Done for assessment report, not for others
F038 | Report - graphical | Add graphical format to other reports e.g. - Pie charts - Bar charts | Could |  | 15 |  |  |  | 50%
F039 | Report - exclude defunct organisations | By default, don't include organisations in reports that no longer exist (can we tell this by their "locked" status? Do we need a (logical) delete? | Could |  | 4
F040 | Upload evidence - drag and drop | Add a drag-and-drop facility to upload evidence | Could |  | 35 |  |  | MIGht not be technically possible - certainly only IE
F041 | Export to XL (platinum) | (Maybe) Includes previous scores for the specific organisation (Maybe) shows differences in widgets from previous year More sophisticated download which provided some of the following: (Maybe) includes colour and formatting (i.e. not just a CSV file) - compromise mIGht be to make it a static document so no need for Excel automation on server. | Could |  | 15
F056 | Report - Status detail | Own organisation report at a detail level i.e. Including individual scores for each widget - option to compare to previous years' scores - option to show target scores - option to include widget text - filter/group by catrgory Show current score and previous years' scores (where comparable/applicable) | Could
F058 | widget authoring - version control/content management | All singing all dancing authoring tool with version control and content management functionality | Could
F063 | Ongoing improvement plans | Facility for XYZs to record the fact that PDs have completed an improvement plan - they do this in DTB as a one-off for PRMB but what about in subsequent years | Could
F066 | Auto notify XYZ when PD submits | Based on XYZ rep info set up in F062 | Could
F072 | PQR InfoSecurity Zone | A place where news and other useful materials can be located - a kind of more specific log-in type webpage than our publicGYwhat's new (ref. Alistair) | Could
F076 | Online feedback | Feedback ("Suggestions") button to allow users to provide feedback e.g. Propose new evidence types (do we really want this kind of feedback?) Accessed via a "contact us" page - and made clear that we do not guarantee to respond. Stored in DB and sent to HIP team members as a weekly dIGest. | Could
F080 | Key widget filters | For all views and reports - consider whether to allow user to apply a "key widgets only" filter (based on the fact that XXX currently has a User Defined View set up to show just the Key widgets) | Could
F088 | Compare assessments across organisations | Ability for HIP team to view the response to a specific widget for multiple organisations (for comparison purposes) | Could
F090 | New Roles re. Bulk E-mails | New roles specifically to allow bulk e-mails to be specific | Could
F094 | Re-send user details | Ability to re-send user their user details and password emails e.g. Because they got their email address wrong the first time round. Also ability to auto send email when change password | Could
F098 | Steering group user role | Add new user role for steering group user - has read-only view of an organisation's assessment | Could
F099 | XYZ report on prisons | Ability for XYZ to get report on Prison toolkit assessments in similar fashion to PDs/Squiddles (this function already exists - but it could be made clearer that XYZs need to set up links with Prisons manually via DTB - perhaps a help function) | Could
F101 | New user role - XYZ report viewer | User role to allow a XYZ user to view PD/Squiddle reports but not view or amend XYZ's own assessment | Could
F103 | XYZs able to see PDs/Squiddles assessments | Specifically, ability to see comments, improvement plans and documents uploaded | Could
F011 | IG portal | A single web page providing links to "all things IG" within PQR EFG and DXX | Could | 0 |  |  |  | External to ExampleApp | 0%
F078 | Extra evidence for audit | Each widget includes extra information about what evidence mIGht be required for audit purposes (require input from Audit Commission for this) | Could |  |  |  | 4
F079 | Indicate audit | An auditor is able to mark an assessment as having been audited on a specific date. This mIGht be at any point during the year (even when the assessment is still in progress) Also to upload the audit report | Could |  |  |  | 7 |  | 100%
F020 | Improved search | Search widgets text including guidance document Search knowledge base documents Manually assIGn keywords to widgets and documents | Could | 10 |  | 10
F077 | Evidence JHYring | User indicates consent to JHYre uploaded evidence. Other users are then able to download it | Could |  |  |  | 20
F043 | WeIGhted widgets |  | Won't
F044 | Single page submission |  | Won't
F045 | Auto populate last year's scores | Only if widget not changed | Won't
F046 | Integrate with risk mgmt tools |  | Won't
F047 | "No change" button | Use as interim measure to indicate nothing has changed | Won't
F048 | Offline toolkit |  | Won't
F049 | Integrate with Performance Accellerator/Proteus |  | Won't
F050 | New version sooner |  | Won't
F064 | PRMB status report | Report showing PRMB status (approved/not approved) for all organisations Available to all (no need to be logged in) Should this be in ExampleApp or not (since PRMB is a DTB thing) Already available in DTB (but do need to log on) | Won't
F069 | Report: Care Quality Commission report | Problems using Pro Clarity - improve it | Won't |  |  |  |  | It's OK - needs licences and training
F081 | Remove attainment levels | Now that we have attainment criteria, ditch the attainment levels and just calculate an overall score based on how many criteria have been fulfilled | Won't
F087 | Collect GHTE details | Collect and store GHTE details in ExampleApp - so we could easily e-mail all GHTEs (e.g. WARP)). Collect details as part of the submission process (get user to validate that the details are still correct if previously entered). | Won't |  |  |  |  | MG not keen to turn the ExampleApp into a contact database
F079 | Report: Board | Report or reports suitable for presenting to the Board. What this is mIGht differ greatly by organisation | Won't | [7 empty] | Duplicate of F017
F022 | Link to "other" KB documents from guidance sheets | Link on guidance document which opens up a list of all KB documents relating to that widget number | Won't | 3 |  | 3
F084 | Squiddlecy bulk registrations | E.g. Boyds can register all their outlets with an account for the same person at HQ (not necessarily a single account though) | Won't
F097 | Remove or hide key widgets | Identifying some widgets as key is confusing because the target for v8 is to achieve level 2 on *all* widgets - get rid of key widgets or hide them | Won't
F100 | XYZ can administer PD/Squiddle assessment | Ability for XYZ admin to perform some admin tasks on PD/Squiddle assessments e.g. Unsubmit | Won't |  |  |  |  | We want to maintain control centrally
F082 | Baseline strateIG | Concern amongst JHYGYLeads and TUG re. Baseline dates/expectations given the level of change for ExampleApp v8 - end of July too early if ExampleApp only goes live end of June We mIGht need a way of allowing users to baseline without having entered their evidence | Won't |  |  |  | 12 |  |  |  | Does the system need any flexibility building in to allow baseline without evidence?
F025 | Report - compare with peers | Report showing progress against selected peers (e.g. Same XYZ, same JHY or individually selected) Include baseline and performance update scores (Perhaps) includes interim (unsubmitted) scores - would need a mechanism for peers to agree to JHYre interim data | Won't | 12 |  | 12 |  | Report 8md Ability to agree to JHYre 4md
F077 | DXX comments | DXX able to add comments to an assessment (at widget level) - these may or may not be visible to applicant and are read only to applicant. | Won't |  |  |  | 4 |  |  |  | Not required now we have a comments field specifically for exemptions
F076 | Improved PD Improvement Planning | Replace/consolidate existing PD improvement planning (currently not very well desIGned) MIGrate tasks into new action planning function? | Won't |  |  |  | 3 |  | 100% | 100% | Nothing extra to do on top of F019
F051 | Update FAQs and notify |  | Operational
F055 | Auto populate last year's evidence | Only if widget not changed Conscious process of confirming evidence still applies for the new year Ability to produce a report which lists evidence items that have expired and are need updating (implies capture of expiry dates for evidence items) | v9
F104 | Administrator's "what's changed" report | A report available to an org admin telling them what has been updated on the assessment since they last logged in - allows them to track progress of updates by users | TBC
F105 | XYZ Provider/Commissioner Split | Split XYZ org type into two (commissioner and provider). Some orgs may need mIGrating from one type to the other | Won't
F106 | Evidence location customisation | Ability for a local admin to restrict which evidence location types are available for their org (to ensure a consistent approach across all widgets) | TBC
F107 | Email address mandatory | Make it mandatory for all users to enter their email address (so we can send out password reminders and mailshots). Include function to capture email address if not present when user first logs in | Could
F108 | XYZs able to track PD/Squiddle improvement plans | Allow XYZs to keep track of which PDs have created improvement plans on an ongoing basis (DTB only allows them to do it in the first year) | TBC
F109
F110
Net Dev Effort (Must & Should) |  |  |  | 202 |  | 30 | 38 |  | 220 | 206
Uncertainty Factor (due to hIGh level widgets) |  |  |  | 40%
Total with Contingency |  |  |  | 282.8
Contingency for Scope Creep |  |  |  | 10%
Total with Contingency |  |  |  | 311.08
Percentage of Baseline Scope |  |  |  | 110% |  |  | 104% |  | 108.9% | 102%
Note on E4: Author: Figure goes in this column if it was 2 "must" or a "should" when we did the baseline estimates

## Progress
Date (w/e) | Original Scope (%) | Contingency (%) | Current Scope (%) | Elab Complete (%) | Dev Complete (%) | Increment
2010-02-19 | 100% | 110% | 150% | 61% | 18% | i2
2010-02-26 | 100% | 110% | 150% | 63% | 27% | i2
2010-03-05 | 100% | 110% | 150% | 68% | 31% | i2
2010-03-12 | 100% | 110% | 150% | 69% | 33% | i3
2010-03-19 | 100% | 110% | 154% | 81% | 40% | i3
2010-03-26 | 100% | 110% | 154% | 82% | 47% | i3
2010-04-02 | 100% | 110% | 154% | 86% | 50% | i4
2010-04-09 | 100% | 110% | 148% | 88% | 53% | i4
2010-04-16 | 100% | 110% | 142% | 89% | 67% | i4
2010-04-23 | 100% | 110% | 142% | 91% | 72% | i5
2010-04-30 | 100% | 110% | 104% | 92% | 77% | i5
2010-05-07 | 100% | 110% | 104% | 94% | 78% | i5
2010-05-14 | 100% | 110% | 104% | 97% | 82% | i5
2010-05-21 | 100% | 110% | 104% | 97% | 82% | i6
2010-05-28 | 100% | 110% | 104% | 97% | 82% | i6
2010-06-04 | 100% | 110% | 104% | 97% | 82% | i6
2010-06-11 | 100% | 110% | 104% | 101% | 85% | i7
2010-06-18 | 100% | 110% | 104% | 101% | 95% | i7
2010-06-25 | 100% | 110% | 104% | 106% | 98% | i7
2010-07-02 | 100% | 110% | 104% | 106% | 98% | i8
2010-07-09 | 100% | 110% | 104% | 106% | 98% | i8
2010-07-16 | 100% | 110% | 104% | 106% | 98% | i8
2010-07-23 | 100% | 110% | 104% | 109% | 102% | i8